## Carquest EDI Integration
App Module | Module | Pct. Complete | Pct. Tested | Description | Comment | In Production (Requires Database Changes)
EDI / EOMS / Freight Calc Core Libraries | Core Shared Library | 85% | 60% | Shared Core Libraries for Database and Other Services shared by all EDI & EOMS Document Translator apps and Fedex Freight and WMS 2021 with EDI Support | Refactored to Latest .Net Version 4.8 | NO
EDI Field Translation Maps 850, 810, 856 for NatOak to Oniel |  | 95% | 30% | Added Additional Fields to Support Carquest EDI with Text Messages, separate BillTo, separate ShipTo |  | NO
Utility Shared Libraries | Core Shared Library | 95% | 90% | Shared Core Libraries for Database and Other Services shared by all EDI/EOMS EZOrdering and WMS | Refactored to Latest .Net Version 4.8 | NO
EDI 850 Inbound Processor (Windows Service) | Windows Server Service | 100% | 95% | Processes inbound 850 Orders, changed to support Carquest Text Fields and Priority flag | Refactored to Latest .Net Version 4.8 | NO
EDI 810 Outbound Processor (Windows Service) | Windows Server Service | 75% | 30% | Processes outbound 810 Invoices, supports new Carquest BillTo, ShipTo and other skdk dkdkdkd dkdkdkdkk dkdkdkdkdkdk dkdkdkd | Refactored to Latest .Net Version 4.8 | NO
EDI 856 Outbound Processor (Windows Service) | Windows Server Service | 30% | 30% | Processes outbound 810 Invoices, supports new Carquest BillTo, ShipTo and other | Refactored to Latest .Net Version 4.8 | NO
EDI Perfection Manual Order (Windows Service- New) | Windows Server Service | 95% | 95% | Reads Carquest Phone/Email Orders Created in Perfection into EDI System, updates and Assigns TransactionID to Perfection | Refactored to Latest .Net Version 4.8 | NO
Update EDI/EOMS CSR Order Editor | Web App | 0% |  | Add Display other Open Orders from same Customer Add Parcel Freight Calculation Feature to Add Freight to Order. | Refactored to Latest .Net Version 4.8
WMS 2021 |  | 35% |  | Upgrade to use .net Latest Version so it can share the EDI and Freight Core Libraries | Refactored to Latest .Net Version 4.8 | NO
| Rebuild Existing WMS 2015 to WMS 2021 Using Core Shared Libraries | 95%
| Aggregate Orders to Same Destination into Groups Shipments | 90% |  | Aggregating orders into Groups/Shipments allows for Orders to bin Finalized together and EDI orders on a single pallet will need no scanning
| Aggregate Orders Remove, Add | 85%
| Recalculate Freight when multiple orders are put in same Parcel Handling Unit | 0% |  |  | Parcel Freight Recalculation 3/22
| Adjust Freight on Aggregated Parcel Orders so Freight is added to largest Invoice, except PD-ACF charges are on individual invoices | 0% |  |  | Parcel Freight Recalculation 3/22
| Finalize Aggregated Orders as Group | 60%
| Scan to Handling Unit (Pallet or Parcel) | 75%
| Scan to Handling Unit Utilities Remove Item from Handling Unit Reset/Clear Scan to Handling Unit | 85%
| Print Carquest Style UCC Label | 100% |  | Needs to be verified
| Print Carquest Style Label from Gun | 85%
| Select Printer by Barcode on Printer | 90%
| Integration of new WMS EDI Features with Existing WMS 2015 code | 90%
| EDI ASN `Handling Unit Packing` Setting | 100% |  | EDI ASN Packing is controlled by a setting per TradingPartner, so that the system will only allow `Handling Unit Packing` if the EDI account requires it. | Not in spec, but is definitely needed
| Mixed Box Packing | 100% |  | Mixed Box Packing is controlled by Perfection Customer Setting. It is allways allowed but the worker is notified the customer does not require Mixed Box Packing | New
| Is On Credit Hold Check, prior to picking | 100% |  | System would error if the order was on credit hold, now does not allow selecting the order. | New