## Carquest EDI Integration
Changed | App Module | Module | Pct. Complete | Pct. Tested | Description | Comment | In Production (Requires Database Changes)
| EDI / EOMS / Freight Calc Core Libraries |  | 95% | 70% | Shared Core Libraries for Database and Other Services shared by all EDI & EOMS Document Translator apps and Fedex Freight and WMS 2021 with EDI Support | Refactored to Latest .Net Version 4.8 | NO
| EDI Field Translation Maps 850, 810, 856 for NatOak to Oniel |  | 95% | 30% | Added Additional Fields to Support Carquest EDI with Text Messages, separate BillTo, separate ShipTo |  | NO
x | Utility Shared Libraries | Core Shared Library | 95% | 90% | Shared Core Libraries for Database and Other Services shared by all EDI/EOMS EZOrdering and WMS | Refactored to Latest .Net Version 4.8 | NO
x | EDI 850 Inbound Processor (Windows Service) | Windows Server Service | 100% | 100% | Processes inbound 850 Orders, changed to support Carquest Text Fields and Priority flag | Refactored to Latest .Net Version 4.8 | YES
| EDI 810 Outbound Processor (Windows Service) | Windows Server Service | 75% | 30% | Processes outbound 810 Invoices, supports new Carquest BillTo, ShipTo and other Fields add for Carquest (ie: priority) | Refactored to Latest .Net Version 4.8 | NO
| EDI 856 Outbound Processor (Windows Service) | Windows Server Service | 60% | 30% | Processes outbound 810 Invoices, supports new Carquest BillTo, ShipTo and other | Refactored to Latest .Net Version 4.8 | NO
x | EDI Perfection Manual Order (Windows Service- New) | Windows Server Service | 100% | 100% | Reads Carquest Phone/Email Orders Created in Perfection into EDI System, updates and Assigns TransactionID to Perfection | Refactored to Latest .Net Version 4.8 | NO
| Update EDI/EOMS CSR Order Editor | Web App | 0% |  | Add Display other Open Orders from same Customer Add Parcel Freight Calculation Feature to Add Freight to Order. | Refactored to Latest .Net Version 4.8
| WMS 2021 |  | 35% |  | Upgrade to use .net Latest Version so it can share the EDI and Freight Core Libraries | Refactored to Latest .Net Version 4.8 | NO
|  | Rebuild Existing WMS 2015 to WMS 2021 Using Core Shared Libraries | 95%
|  | Aggregate Orders to Same Destination into Groups Shipments | 90% |  | Aggregating orders into Groups/Shipments allows for Orders to bin Finalized together and EDI orders on a single pallet will need no scanning
|  | Aggregate Orders Remove, Add | 85%
|  | Recalculate Freight when multiple orders are put in same Parcel Handling Unit | 0% |  |  | Parcel Freight Recalculation 3/22
|  | Adjust Freight on Aggregated Parcel Orders so Freight is added to largest Invoice, except PD-ACF charges are on individual invoices | 0% |  |  | Parcel Freight Recalculation 3/22
|  | Finalize Aggregated Orders as Group | 60%
|  | Scan to Handling Unit (Pallet or Parcel) | 75%
|  | Scan to Handling Unit Utilities Remove Item from Handling Unit Reset/Clear Scan to Handling Unit | 85%
|  | Print Carquest Style UCC Label | 100% |  | Needs to be verified
|  | Print Carquest Style Label from Gun | 85%
|  | Select Printer by Barcode on Printer | 90%
|  | Integration of new WMS EDI Features with Existing WMS 2015 code | 90%
x |  | EDI ASN `Handling Unit Packing` Settings | 100% | 100% | EDI ASN Packing is controlled by a setting per TradingPartner, so that the system will only allow `Handling Unit Packing` if the EDI account requires it. | Not in spec, but is definitely needed
x |  | Mixed Box Packing | 100% | 100% | Mixed Box Packing is controlled by Perfection Customer Setting. It is allways allowed but the worker is notified the customer does not require Mixed Box Packing | New
x |  | Is On Credit Hold Check, prior to picking | 100% | 100% | System would error if the order was on credit hold, now does not allow selecting the order. | New

## Sheet2
0%
EDI/EOMS/Freight Calc Core Libraries: Shared Core Libraries for Database and Other Services shared by all EDI & EOMS Document Translator apps, Fedex Freight and WMS 2021 with EDI Support | 95% | 10% | 95
EDI Field Translation Maps 850, 810, 856 for NatOak to Oniel: Added Additional Fields to Support Carquest EDI with Text Messages, separate BillTo, separate ShipTo | 95% | 0% | 95
Utility Shared Libraries: Shared Core Libraries for Database and Other Services shared by all EDI/EOMS EZOrdering and WMS | 95% | 0% | 95
EDI 850 Inbound Processor (Windows Service): Processes inbound 850 Orders, changed to support Carquest Text Fields and Priority flag | 100% | 0% | 100
EDI 810 Outbound Processor (Windows Service): Processes outbound 810 Invoices, supports new Carquest BillTo, ShipTo and other | 75% | 0% | 75
EDI 856 Outbound Processor (Windows Service): Processes outbound 856 Invoices, supports new Carquest BillTo, ShipTo and other | 60% | 30% | 60
EDI Perfection Manual Order (Windows Service- New): Reads Carquest Phone/Email Orders Created in Perfection into EDI System, updates and Assigns TransactionID to Perfection | 100% | 5% | 100
Updated EDI/EOMS CSR Order Editor: Add display other open orders from same customer; Add parcel freight calculation feature to add freight to order. | 0% | 0% | 0
Rebuild Existing WMS 2015 to WMS 2021 Using Core Shared Libraries | 95% | 0% | 95
Aggregate Orders to Same Destination into Groups | 90% | 0% | 90
Aggregate Orders Remove, Add | 85% | 0% | 85
Recalculate freight when multiple orders are put in same Parcel Handling Unit | 0% | 0% | 0
Adjust Freight on aggregated parcel Orders so freight is added to largest invoice, except PD-ACF charges are on individual invoices | 0% | 0% | 0
Finalize Aggregated Orders as Group | 60% | 0% | 60
Scan to Handling Unit (Pallet or Parcel) | 75% | 0% | 75
Scan to Handling Unit Utilities, Remove Item from Handling Unit. Reset/Clear Scan to Handling Unit | 85% | 0% | 85
Print CARQUEST Style UCC Label | 100% | 0% | 100
Print CARQUEST style label from gun | 85% | 0% | 85
Select printer by barcode on printer | 90% | 0% | 90
Integration of new WMS EDI Features with Existing WMS 2015 code | 90% | 70% | 90
EDI ASN “Handling Unit Packing Setting | 100% | 0% | 100
Mixed Box Packing | 100% | 0% | 100
Is on Credit Hold Check, prior to picking | 100% | 0% | 100

## Sheet1 (hidden)
ID | Software Program | Update | New Features | Expected Completion Date
1 | WMS 2021 Software | Update to Existing Software and New Software | EDI Packing to Pallets for Carquest Printing UCC128 EDI Labels from Guns Grouping Orders into Shipments (multiple orders), Finalizing Grouped Orders as One (Shipment) Parcel Freight Recalculation of Shipments | 2021-05-24
2 | EDI 850 Inbound Software - Imports EDI Customer PO's | Update to Existing Software | Capturing text messages for display to CSR's and Warehouse | 2021-04-13
3 | EDI 810 Software - Sends EDI Invoices | Update to Existing Software | Changes to incorporate BillTo addresses in addition to the ShipTo addresses | 2021-04-15
4 | EDI 856 Software - Sends Advance Ship Notices (ASN) | Update to Existing Software | Adding pallet level itemization and | 2021-05-30
5 | EDI Perfection Manual Order | New Software | Creates EDI Orders from orders manually entered into Perfection | 2021-04-22
6 | EDI/EOMS CSR Order Editor | Update to Existing Software | EDI/EOMS CSR Order Editor Updates to display other pending EDI Orders from Carquest, messages that are being sent in on EDI PO's | 2021-05-31